## Project Plan
Implementation Project Plan
PROJECT TITLE | Talkdesk Implementation |  |  |  | COMPANY NAME | EGIA
PROJECT MANAGER | Samantha | Sanchez |  |  | OVERALL TIMELINE | December 2025 - March 2026
SOLUTIONS CONSULTANT | Danielle | Abbott |  |  | LAST UPDATED | 2026-02-08
(Indicates Key Project Milestone) |  |  |  | Key Durations
TASK TITLE / DESCRIPTION | TASK OWNER | START DATE | END DATE | DURATION (working days) | PCT OF TASK COMPLETE | AT RISK? | NOTES/ STATUS | DETAILS /INFORMATION
Project Communication |  | 2025-11-24 | 2025-11-24 |  | 100%
Implementation Kick off | Samantha | 2025-11-24 | 2025-11-24 | 1 | 100% | FALSE |  | Project kickoff meeting
Holidays/ Time-Off
Thanksgiving Day & Next | Talkdesk | 2025-11-27 | 2025-11-28 | 2 | 100% | FALSE
Christmas Eve & Day | Talkdesk | 2025-12-24 | 2025-12-25 | 2 | 0% | FALSE
New Years Day | Talkdesk | 2026-01-01 | 2026-01-01 | 1 | 0% | FALSE
President's Day | Talkdesk | 2026-02-16 | 2026-02-16 | 1 | 0% | FALSE
Discovery |  | 2025-11-25 | 2026-01-22 |  | 100%
Discovery Workshop(s) | Danielle | 2025-11-25 | 2025-12-12 | 14 | 100% | FALSE | Scheduled | Workshop to detail requirements to feed discovery report and begin config
Complete Discovery WorkBooks | EGIA | 2025-11-25 | 2025-12-12 | 14 | 100% | FALSE |  | Fill out configuration workbook for requirements gathering
Complete Discovery Report | Danielle | 2025-12-15 | 2025-12-26 | 10 | 100% | FALSE |  | Fill out discovery report based on information gathered
Approval of Discovery Report | EGIA | 2025-12-29 | 2026-01-22 | 19 | 100% | FALSE |  | (email) Sign-off on discovery and requirements gathering. Grants approval to move to Configuration stage
Configuration |  | 2026-01-23 | 2026-02-20 |  | 77%
Move KBs from Intent based to Agentic | Danielle | 2026-01-23 | 2026-01-23 | 1 | 100% | FALSE
Build/Configure Agentic AI (FAQ) | Danielle | 2026-01-26 | 2026-02-06 | 10 | 100% | FALSE |  | https://talkdesk.atlassian.net/wiki/spaces/SC/pages/5377654792/AI+-+Agent+Platform+-+CX+Product+Page
Build/Configure Agentic AI (Rebate) | Danielle | 2026-01-26 | 2026-02-20 | 20 | 50% | FALSE | Remaining steps is set up rebate lookup, and have AI split for Tampa vs | https://talkdesk.atlassian.net/wiki/spaces/SC/pages/5377654792/AI+-+Agent+Platform+-+CX+Product+Page
Create a Mutli-Agent on AI Platform | Danielle | 2026-01-26 | 2026-01-28 | 3 | 100% | FALSE
Create Agentic Autopilot | Danielle | 2026-01-28 | 2026-01-30 | 3 | 100% | FALSE
Connect Agentic Autopilot to Studio | Danielle | 2026-01-30 | 2026-02-02 | 2 | 100% | FALSE
Configure Channels | Danielle | 2026-02-02 | 2026-02-03 | 2 | 100% | FALSE
Configure Voices | Danielle | 2026-02-03 | 2026-02-04 | 2 | 100% | FALSE
QA Agentic AI Agent | Danielle | 2026-02-09 | 2026-02-13 | 5 | 20% | FALSE |  | Fuctionality testing and acceptance
Configurations Complete |  | 2026-02-13 | 2026-02-13 | 0 | 0% | FALSE
Test, Train, and Prepare |  | 2025-11-24 | 2026-03-13 |  | 4%
Talkdesk Academy - Agentic AI | EGIA | 2025-11-24 | 2026-02-13 | 60 | 10% | FALSE |  | Autopilot - Agentic ¦ Admins ¦ Learning Paths ¦ Talkdesk Academy
AI Training | Danielle | TBD | TBD | 1 | 0% | FALSE |  | Live Indepth Training
Build out test plan | TD/EGIA | 2026-02-09 | 2026-02-13 | 5 | 10% | FALSE | Need to tailor to EGIA | Test plan for UAT
UAT Handoff | TD | 2026-02-13 | 2026-02-13 | 1 | 0% | FALSE | To schedule
User Acceptance Testing (UAT) | EGIA | 2026-02-16 | 2026-03-13 | 20 | 0% | FALSE |  | UAT Window
Deploy |  | 2026-03-13 | 2026-04-24 |  | 0%
Complete pre-golive checklist and final sanity tests | TD/EGIA | 2026-03-13 | 2026-03-13 | 1 | 0% | FALSE
Go Live Deployment | TD/EGIA | 2026-03-16 | 2026-03-16 | 1 | 0% | FALSE |  | Talkdesk will provide support for up to one (1) go-live event(s) (i.e. cutovers).
Post Deployment Support | Danielle | 2026-03-16 | 2026-04-24 | 30 | 0% | FALSE |  | Post go-live, the Delivery Resource(s) will stay engaged for up to six (6) weeks for ongoing support.
AI Optimization | AI Team | TBD | TBD | 0 | 0% | FALSE |  | Talkdesk will provide continued AI Optimization services, for a period of up to three (3) months.
Official Transition to Support/Services | TD | 2026-04-24 | 2026-04-24 | 1 | 0% | FALSE |  | CSM/TAM become primary point(s) of contact
Project Closure | Samantha | 2026-04-24 | 2026-04-24 | 0 | 0% | FALSE
Formulas:
Sanchez = MIN([Sanchez, row below])
Sanchez = MIN([Sanchez, row below]:D21)
END DATE = MAX([END DATE, row below])
END DATE = if([Sanchez]="","",IF([DURATION (working days)]<=1, [Sanchez], WORKDAY([Sanchez], [DURATION (working days)]-1)))

## SOW
Phase 1
Elite License | Product | SOW Terms | Status | Notes
Agentic Autopilot (FAQ): Talkdesk will configure one (1) Agentic Autopilot, assuming the following scope: ○ Included Channels: ○ Voice ○ Digital (Chat) Talkdesk Inc. ¦ 440 N Barranca Avenue #4375 Covina, CA 91723 ¦ +1.844.332.2859 Docusign Envelope ID: 41240137-EE3D-47AB-8348-0A14AEB56FCA ○ Agentic Autopilot Goals: ○ Provide General information (FAQs) ○ Understand the caller’s / written message’s intent and identify/respond in the contact’s language. ○ FAQ detection based on the use of Search Knowledge component with content configured in the Talkdesk Knowledge Management. ○ Includes External Sources with a web crawler of up to ten (10) seed URLs, with up to two (2) page levels deep, and up to one hundred (100) links per page. ○ Talkdesk will provide testing support and prompt fine-tuning for up to ten (10) FAQs per Agentic. ○ Client is responsible for testing additional Q&As configured in the solution. ○ If the FAQs do not resolve the question, Talkdesk will escalate the conversation to a Studio Flow for basic routing to a Ring Group or an Agent. ○ Includes up to one (1) Action path to be used for escalations. ○ Talkdesk's Responsibilities: ○ Configuration of the AI Agent Orchestrator prompts (Name, Description, and Instructions) ○ Context variables creation and description (as applicable) ○ Configuration of up to one (1) AI Agent(s) for specific instructions (as applicable). ○ Configuration of up to ten (10) Knowledge Management Cards or External Sources (PDF files / Web Crawler URLs); ○ Client’s Responsibilities: ○ Client will be required to build, manage and maintain the external articles accordingly or can use the Talkdesk Knowledge Management product as an in-house knowledge solution for the FAQs. ○ Client is responsible for providing the descriptions (ie. instructions to the LLM model) for the Automation Goal, Variables, and Actions. ○ During the testing phase and after going live, Client will be responsible for fine tuning descriptions as required. ○ For the API calls mentioned above, assume the Client will provide REST APIs that meet the minimum requirements for the use case. See Talkdesk Connections integration assumptions in Section V. Talkdesk Inc. ¦ 440 N Barranca Avenue #4375 Covina, CA 91723 ¦ +1.844.332.2859 Docusign Envelope ID: 41240137-EE3D-47AB-8348-0A14AEB56FCA ○ Product is part of a Preview program, not all features and functionality will be available. ○ Note: Any Autopilot integrations, advanced features, or experiences beyond the above scope are not included in this engagement. Additional requirements will need a Change Order.
Future Phases

## Milestones
Milestones | PCT Complete | Closed Date
Contract Signing | 100%
Implementation Kick off | 100% | 2025-11-24
Approval of Discovery Report | 100% | 2026-01-22
Configurations Complete | 0% | 2026-02-13
User Acceptance Testing (UAT) | 0% | 2026-03-13
Go Live Deployment | 0% | 2026-03-16
Official Transition to Support/Services | 0% | 2026-04-24

## Action Items Tracker
Action Items Tracker
Status | Category | Description | Action Owner | Expected Resolution Date | Comments
Closed | Discovery | Send availability for 3 discovery sessions (first two weeks of December) Eddie prefers Tuesdays/Wednesdays, afternoons, 1-3 PM PST | Samantha | 2025-11-26
Closed | Project Management | Provide SharePoint access by Wednesday | Clinton | 2025-11-26
Closed | Discovery | Complete discovery questionnaire and workbooks | EGIA team | 2025-12-05
Closed | Project Management | Review existing project documentation to avoid duplication | Samantha | 2025-11-26
Closed | Discovery | Lead technical discovery sessions | Danielle | 2025-12-05
Closed | Discovery | Provide training documentation for MET and TBW systems to Danielle. | Clinton / Maria | 2025-12-05
In Progress | Discovery | Provide list of websites (public & internal KB) that Agentic AI should reference. | Clinton / Maria | 2025-12-05 | Verify website
In Progress | Discovery | Confirm/update FAQs to ensure accuracy for card conversion. | Clinton / Maria | 2025-12-05 | Verify if completed
Closed | Discovery | Complete Salesforce licensing validation and coordinate with Salesforce admin to begin integration setup. | Clinton / Maria | 2025-12-05 | Documentation has been provided; Clinton has internal meeting on 12/16 with his team to work through this
Closed | Discovery | Provide preferred AI name (final) after checking with leadership/marketing. | Clinton / Maria | 2025-12-05
In Progress | Discovery | Prepare automations list (up to 2 initial automations) for Talkdesk to build. | Clinton / Maria | 2025-12-05
In Progress | Discovery | Send any additional guardrails or conversational tone guidelines. | Clinton / Maria | 2025-12-05
Open | Configs | Convert existing FAQs into Knowledge Cards for Agentic AI. | Danielle | TBD
Open | Configs | Begin early framework setup using: Voice configuration Preliminary name (“Ageia”) Web sources once provided | Danielle | TBD
Open | Configs | Prepare initial AI flow structure using current Autobot as baseline. | Danielle | TBD
Closed | Training | Provide training on creating additional Salesforce automations (after EGIA completes integration). | Danielle | TBD
Closed | Project Management | Deliver a “laundry list” of required items for Friday’s follow-up session. | Sam | 2025-12-05
In Progress | Discovery | Upload remaining training documentation if found | Clinton | 2025-12-09
Open | Discovery | Coordinate scheduling of interview with Angela & Lori | Clinton | 2025-12-09 | High on the list of priority
Closed | Discovery | Contact Salesforce team (Mauricio or Justin) to confirm POC and required setup steps | Clinton | 2025-12-08
Closed | Discovery | Review uploaded documentation and identify any gaps | Danielle | 2025-12-09
Closed | Discovery | Begin drafting Discovery Report (BRD) | Danielle | 2025-12-09
Open | Discovery | Determine setup requirements, upload instance, and schedule meeting with Danielle if needed | Salesforce Team | TBD
Open | Discovery | Review all uploaded documentation (dispositions, processing steps, status codes) | Danielle | 2026-12-31
Open | Discovery | Evaluate old Talkdesk configuration/scripts for reuse | Danielle | 2026-12-31
Closed | Discovery | Confirm Salesforce licensing activation | Clinton | 2026-12-19
Closed | Discovery | Include Danielle in Salesforce integration meeting | Clinton | 2026-12-12
Closed | Discovery | Identify gaps/questions requiring EGIA clarification | Danielle | 2026-12-19
Open | Discovery | Follow up with Lori if clarification is needed on status messaging | Clinton | 2026-12-31
Closed | Discovery | Review Discovery Report with Eddie | Clinton | 2026-01-14
Monitoring | Discovery | Provide formal Discovery approval via email | Clinton | 2026-01-14
In Progress | Configs | Begin configuration work post-approval | Danielle | 2026-01-15
Closed | Project Management | Start weekly project status reports (including hours) | Samantha | 2026-01-12
Closed | Discovery | Investigate Nimble-compatible CRM integration options | JJ | 2026-01-16
Closed | Discovery | Review contractual flexibility if CRM integration is removed | JJ | 2026-01-16
Closed | Discovery | Follow up on Discovery approval if not received | Samantha | 2026-01-14
Closed | Discovery | Reschedule Discovery Report review with Eddie present | Danielle | 2026-01-16
Closed | Discovery | Review Discovery Report alignment with initiatives | Eddie | 2026-01-21
Closed | Discovery | Confirm Salesforce / Nimble integration status with JJ | Clinton | 2026-01-16
Closed | Discovery | Follow up with JJ to prompt response on integration | Danielle | 2026-01-16
Closed | Project Management | Add Samantha Sanchez to rescheduled invite (FYI) | Danielle | 2026-01-16
Closed | Discovery | Provide approval once Eddie confirms alignment | Clinton | 2026-01-22

## IssuesRisks Tracker
Issues / Risks Tracker
Status | Type | Severity | Action Owner | Category | Description | Expected Resolution Date | Comments | Ticket # (Zendesk or Jira)

## Contacts
Talkdesk Implementation - Contacts
| Company | Name | Email | Role
| Talkdesk | JJ Needham | jj.needham@talkdesk.com | EMEA Account Executive
| Talkdesk | Danny Orrick | danny.orrick@talkdesk.com | Client Success Manager
| Talkdesk | Jason Koval | jason.koval@talkdesk.com | PS Architect
| Talkdesk | Samantha Sanchez | samantha.sanchez@partner.talkdesk.com | Project Manager
| Talkdesk | Danielle Abbott | danielle.abbott@partner.talkdesk.com | Solutions Consultant
| Talkdesk | N/A |  | Technical Account Manager
PST
| EGIA | Clinton Cramer | ccramer@egia.org | Director - IT Program Management
| EGIA | Maria Alatorre | malatorre@egia.org
| EGIA | Eddie Javaid | ejavaid@egia.org | Chief Technology Officer
EGIA

## Hours Logged
(As of 2026-02-06)
| Initial SOW Hours | Change Order Hours | Total Budget Hours | Actual Hours Consumed To-Date | % of hours consumed To-Date
Total Implementation | 163 | 0 | 163 | 59.25 | 36.35%
*Please see SOW for details on the estimated budget. These hours will be invoiced monthly at the hourly rate.
2026-02-06
| SOW | Actuals | % Actuals
Project Communication | 45 | 26.75 | 59.44%
Discovery | 11 | 17.75 | 161.4%
Configuration | 31 | 14.75 | 47.58%
Testing | 54 | 0 | 0%
Training | 2 | 0 | 0%
Deployment | 20 | 0 | 0%
Total | 163 | 59.25 | 36.35%

## Go Live Checklist
| EGIA |  | Go Live Checklist
Task | Owner | Status | Notes
Agent Preparation
All agents confirmed as added to production | EGIA | FALSE | # of agents confirmed and configured in Talkdesk
Agents properly trained and ready | EGIA | FALSE | TD Academy eLearnings complete
Microphone settings & headset compatibility confirmed | EGIA | FALSE | Connectivy Checks Windows Users: Documentation LINK HERE
Agent validated TD Conversations works with both IB/OB calls | EGIA | FALSE | Agent Workspace & Conversations App are installed and active for all agents
Local network tests and assessment complete | EGIA | FALSE | We need to have at least a sample of agents (the more the merrier), complete our network test. Run at least 3 network tests, per-site, on 3 different periods of the day and spreadsheet info filled in accordingly. TD VE advised on any notable optimizations to be implemented for go live
Continuity Settings defined / configured | EGIA | FALSE | Continuity settings configured and available in the event of a service disruption
Integrations
Integration system(s) pushed to production | All Parties | FALSE | Integrations moved from Dev/SB to Prod environment Ex: Salesforce, Zendesk, etc
Validate automation tasks working in production | EGIA | FALSE | Test if automations are working in live environment (ex: ticket creation, ticket updates, etc.)
Business Preparation
Complete UAT Testing Guide | EGIA | FALSE | All rows in UAT guide marked as 'Y'
Complete operational analysis / cutover plan | EGIA | FALSE | Admins/supervisors understand business objectives and deployment strategy for new solution relating to cutover
Go/No-Go Decision | All Parties | FALSE | Solidify Go Live Date/Time
Schedule Go-Live Support Bridge | Talkdesk | FALSE | TD PM to confirm go live support bridge (remote via Teams) - invites sent
Go Live on Talkdesk Platform | All Parties | FALSE | All tasks above should be marked 'complete' by this time - calls are coming thorugh to the TD platform