## INFO
User Story Guide Info Sheet
DELETE OR HIDE THIS TAB ONCE REVIEWED
Purpose of this Document
This document serves to manage and monitor all Client User Stories & Test Items. This document is created by the SC assigned to the project and completed with the client.
How To | Step by Step
Add New Line on UAT Summary for New Sheet | Type new sheet name in Column B for User Stories OR Column G for Studio Flows.
IMPORTANT: Spelling must be EXACTLY the same on new sheet & new line
Highlight cells for "Complete, Open Issues, & Completed Tasks" in line above
Copy
Paste in the line below to copy the formula down to your newly added line
Hyperlink new row's sheet name to the new tab by the same name
Add New Sheet | Select sheet that most closely resembles how you want your new sheet to look.
Right Click
Duplicate Sheet
Rename Duplicated Sheet
NOTE: Sheet colors correspond with User Story Type
PRO TIP: When ADDING: Add row on UAT Summary FIRST, then add sheet. Summary Tab will ALWAYS show you if you have a discrepancy if you work in this order.
Remove Unneeded Sheets | Right click sheet you don't need.
Delete :)
Will need to remove the corresponding rows on UAT Summary
PRO TIP: When REMOVING: Remove sheet FIRST, then row on UAT Summary. Summary Tab will ALWAYS show you if you have a discrepancy if you work in this order.
Functionality | Info
Sheet Names/Summary | Sheet names MUST be exactly the same text as listed on UAT summary.
Formulas on UAT Summary Tab will be looking for a sheet with a matching name.
Hidden Columns & Rows | In each sheet, there are hidden columns all the way to the right hand side & hidden rows at the top
These are critical to keep so the formulas remain dynamic from individual testing sheets to summary
DO NOT DELETE!
Check Mark Boxes | Total number of tasks is calculated by the number of check mark boxes in each test sheet.
Be sure that you only have checkboxes on rows where there is a test to perform.
Formulas | Any cell where you see a formula - DO NOT DELETE
Formulas on UAT Summary Tab will copy downward, not sideways.
Functionality | Info
Consulting Studio Flow Component values | Professional Services Wiki

## UAT Summary
User Story Guide Summary
User Story Guide is complete when all squares are 'green/yes' which signifies Go Live readiness and all Acceptance Criteria has been met
| Overall Tasks Complete: |  |  | 0 of 57
| Overall Percent Complete: |  |  | 0% |  | THESE COLUMNS SHOULD BE HIDDEN - DO NOT DELETE COLUMNS OR ROWS
USER STORIES
| Talkdesk User Stories | UAT Ready Status | Complete | Open Issues | Completed Tasks | Total Complete | Total Tasks
| Agentic AI User Stories (FAQs) | Ready for UAT | NO | 0 | 0 of 52 | 0 | 52
| Client User Stories | Not Ready for UAT | NO | 0 | 0 of 5 | 0 | 5
[6 empty] | 0 | 57

## Agentic AI User Stories (FAQs)
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 52
[9 empty] | Total Tasks | 52
[9 empty] | Total Ready | 52
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - Audience / Virtual Agent |  |  |  |  | UAT Summary
Note: This tab contains functions related to Virtual Agent |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story | Acceptance Criteria / How to Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| As a live chat customer/caller, I want to be able to...... | Testing Number: +1(916)993-3367
| Get information on Water Savings Incentive Program (WSIP) | - Call into the test number - When prompted by VA ask about the Water Savings Incentive Program (WSIP) - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Turf Replacement | - Call into the test number - When prompted by VA ask about Turf replacement - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Public Agency | - Call into the test number - When prompted by VA ask about Public Agency - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Dead Grass replacement | - Call into the test number - When prompted by VA ask about Dead Grass replacement - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Synthetic Turf | - Call into the test number - When prompted by VA ask about Synthetic Turf - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Sustanable Features | - Call into the test number - When prompted by VA ask about Sustanable Features - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Approved Plants | - Call into the test number - When prompted by VA ask about Approved Plants - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Parkway | - Call into the test number - When prompted by VA ask about Parkway - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Rebates with Third Parties | - Call into the test number - When prompted by VA ask about Sustanable Features - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Multi-Address Tracking sheet (LA Permit) | - Call into the test number - When prompted by VA ask about Multi-Address Tracking sheet (LA Permit) - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on approved Toilet Models | - Call into the test number - When prompted by VA ask about Toilet Models - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Smart Controllers | - Call into the test number - When prompted by VA ask about Smart Controllers - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Free Installs of sprinklers | - Call into the test number - When prompted by VA ask about Free Installs - Information should only be provided for Tampa | TRUE | FALSE | FALSE
| Get information on Weather Irrigation rebates | - Call into the test number - When prompted by VA ask about Weather Irrigation rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Shallow Well rebates | - Call into the test number - When prompted by VA ask about Shallow Well rebates - Information should only be provided for Tampa | TRUE | FALSE | FALSE
| Get information on Licensed irrigation contractors | - Call into the test number - When prompted by VA ask about Licensed Irrigation contractors - Information should only be provided for Tampa | TRUE | FALSE | FALSE
| Get information on On-site Retrofit Program | - Call into the test number - When prompted by VA ask about On-site Retrofit Program - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on funding for WaterWise and WaterSmart programs | - Call into the test number - When prompted by VA ask about funding for WaterWise and WaterSmart programs - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Turf Removal | - Call into the test number - When prompted by VA ask about Turf Removal - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Hose Bib rebates | - Call into the test number - When prompted by VA ask about Hose Bib rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Rotating Nozzle rebates | - Call into the test number - When prompted by VA ask about Rotating Nozzle rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Cistern rebates | - Call into the test number - When prompted by VA ask about Cistern rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Rain Barrel rebates | - Call into the test number - When prompted by VA ask about Rain Barrel rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Flow Monitor rebates | - Call into the test number - When prompted by VA ask about Flow Monitor rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Clothes Washer rebates | - Call into the test number - When prompted by VA ask about Clothes Washer rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on WaterSense-certified weather based irrigation controller rebates | - Call into the test number - When prompted by VA ask about WaterSense-certified weather based irrigation controller rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get infromation on WaterSense-certified soil moisture sensor rebates | - Call into the test number - When prompted by VA ask about WaterSense-certified soil moisture sensor rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Rotating Sprinkler rebates | - Call into the test number - When prompted by VA ask about Rotating Sprinkler rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Plumbing Flow rebates | - Call into the test number - When prompted by VA ask about Plumbing Flow rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Urinal rebates | - Call into the test number - When prompted by VA ask about Urinal rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on High Efficiency Toilet rebates | - Call into the test number - When prompted by VA ask about High Efficiency Toilets rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Rotary Nozzel rebates | - Call into the test number - When prompted by VA ask about Rotary Nozzel rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Shower Head rebates | - Call into the test number - When prompted by VA ask about Shower Head rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Faucet Aerator rebates | - Call into the test number - When prompted by VA ask about Faucet Aerator rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Flow Regulator rebates | - Call into the test number - When prompted by VA ask about Flow Regulator rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Ice Machine rebates | - Call into the test number - When prompted by VA ask about Ice Machine rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Food Steamer rebates | - Call into the test number - When prompted by VA ask about Food Steamer rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Vaccum Pump rebates | - Call into the test number - When prompted by VA ask about Vaccum Pump rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Cooling Controller rebates | - Call into the test number - When prompted by VA ask about Cooling Controller rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Cooling Tower rebates | - Call into the test number - When prompted by VA ask about Cooling Tower rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get infromation on Central Computer Irrigation Controller rebates | - Call into the test number - When prompted by VA ask about Central Computer Irrigation Controller rebates - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Project Inspection | - Call into the test number - When prompted by VA ask about Project Inspection - Information should only be provided for SoCal (Commercial & Residential) & Tampa | TRUE | FALSE | FALSE
| Get information on Property Call | - Call into the test number - When prompted by VA ask about Property Call - Information should only be provided for SoCal (Commercial & Residential) & Tampa | TRUE | FALSE | FALSE
| Get information on Multiple Addresses on a Single Meter | - Call into the test number - When prompted by VA ask about Multiple Addresses on a Single Meter - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Multiple device rebates | - Call into the test number - When prompted by VA ask about Multiple device rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Multi-Family Application rebates | - Call into the test number - When prompted by VA ask about Multi-Family Application rebates - Information should only be provided for Tampa | TRUE | FALSE | FALSE
| Get information on Hotel Application rebates | - Call into the test number - When prompted by VA ask about Hotel Application rebates - Information should only be provided for Tampa | TRUE | FALSE | FALSE
| Get information on Residential Application rebates | - Call into the test number - When prompted by VA ask about Residential Application rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information on Commercial Application rebates | - Call into the test number - When prompted by VA ask about Commercial Application rebates - Information should only be provided for SoCal | TRUE | FALSE | FALSE
| Get information for Landlord not on Bill | - Call into the test number - When prompted by VA ask about Landlord not on Bill - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on why you need a water bill | - Call into the test number - When prompted by VA ask about why you need a water bill - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE
| Get information on Rebate Taxability | - Call into the test number - When prompted by VA ask about Rebate Taxability - Information should only be provided for SoCal & Tampa | TRUE | FALSE | FALSE

## Client User Stories
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 5
[9 empty] | Total Tasks | 5
[9 empty] | Total Ready | 0
[9 empty] | UAT Ready Status | Not Ready for UAT
User Stories - Client User Stories |  |  |  |  | UAT Summary
|  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story As an Agent, I want to be able to...... | Acceptance Criteria / How To Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE

## Issue Log
Date Identified | Issue Status | Date Resolved | Severity | Issue Description | Interaction ID | FAQ Source | Issue Owner | Notes