Bridgepoint Meeting Notes

| Subject: Talkdesk Implementation Project Kickoff | DATE: 11/7/2024 |
| --- | --- |
| Agenda: - Introductions - Project Scope & Project Plan - Implementation Overview - Next Steps - Best Practices and Resources | Attendees: - Samantha Sanchez - Tristan Bateman - Clinton Cramer - Nathaniel Odom |

## Helpful Links: (currently attaching everything by email at this time, need to create a collaborate workspace and will link everything once that is complete)

- Meeting Recording

- Project OneDrive

- Kickoff Deck

- Project Plan

- Data Collection Workbook

## Action Items:

| ## Team | ## Item/Deliverable | ## Who | ## Due Date |
| --- | --- | --- | --- |
| ## EGIA | ## Complete Talkdesk Academy Training | ## ALL | ## 12/6/2024 |
| ## EGIA | ## Start filling out the Data Collection Workbook | ## ALL | ## 11/12/2024 |
| ## EGIA | ## Complete the Network Test | ## ALL | ## 11/21/2024 |
| ## BPT | Share Project Documentation | ## Samantha | ## Complete |
| ## BPT | Share Data Collection Workbook | ## Samantha | ## Complete |
| ## BPT | Schedule Discovery Sessions (2-3) | ## Samantha | ## Complete |
| ## BPT | Schedule Weekly Review Meetings | ## Samantha | ## 11/15/2024 |

Notes:

- Introductions

  - Bridgepointe CX (BPT)

    - Samantha Sanchez – Project Manager

      - Main Point of Contact

      - 1st point of escalation

    - Tristan Bateman – Sr Solutions Consultant

      - Technical Resource

    - Kim Waters – CSS Manager

      - 2nd point of escalation

  - EGIA

    - Clinton Cramer – wears many hats

      - Main Point of Contact

    - Nathaniel Odom – Service Desk Manager + additional

  - Scope

    - Services

      - Inbound/Outbound Voice

      - Talkdesk Phone

    - Integrations

      - Standard Talkdesk Connections

    - Connectivity

      - WebRTC

      - Talkdesk CX Cloud App

        - Conversations/Agent Workspace

    - Inbound Flow

      - 1 Studio Flow

    - Agent Count

      - 55 agents

    - Additional Features

      - Proactive Notifications

      - Autopilot

      - Customer Experience (Interaction) Analytics

    - Numbers

      - Porting Numbers and Purchasing 1 New Talkdesk Number

- High Level Plan

  - Project Kickoff – 11/7/2024

  - P1 Discovery Report Approval – 11/22/2024

  - Configurations Complete – 12/4/2024

  - UAT Complete – 12/20/2024

  - Go Live – 12/23/2024

    - EGIA would like to move as quickly as possible as they are on Month-to-Month plan with their current Vendor. BPT expressed we can go as quick as they would like as long as they are actively involved.

    - Drop dead date is 1/15/2025

- Implementation Overview

  - Cadence of Implementation Activities

  - Communication and Collaboration

  - All meetings will be recorded, and notes will be accessible in the project drive.

  - Reviewed Project Plan

- Next Steps

  - BPT

    - Share Project Documentation

    - Share Data Collection Workbook

    - Schedule Discovery Sessions - done

    - Schedule Weekly Check Ins

  - EGIA

    - Complete Talkdesk Academy Training role-based certification

    - Begin filling out Data Collection Workbook

      - Ideal to complete prior to 1st Discovery Session

    - Complete the Network Test – will be sending a separate email that will include details on the network settings and the network test link specific to EGIA

- Best Practices

  - Use Google Chrome - Always use the most recent version.

    - Edge has also recently become compatible with Talkdesk.

  - No Chrome Plugins - Avoid plugins (Ad Blocker) and extensions.

  - Enable Microphone - Allow microphones in your computer settings.

  - Use 3.5mm Audio - Ensure headsets use 3.5mm jacks and not USB.

  - Ethernet Connection - Use a wired connection instead of a wi-fi.

  - Save CPU - Network-intensive apps can compete with audio bandwidth.

  - Port or Purchase - Can choose to port existing or purchase new numbers.

- Resources

  - Talkdesk Release Notes & Weekly Digest

    - Managers and Administrators should subscribe to receive email updates.

  - Talkdesk Status

    - Managers and Administrators should subscribe to receive email updates.

  - Talkdesk Academy

  - Installing CX Cloud & Agent Workspace

  - Number Porting

  - Network Test

  - System Requirements & Network Settings

  - Talkdesk Integrations

  - Set Up Browser

  - Recommended Headsets