## Porting Tracking
Carrier | Phone Number | FDW | Forward to | Friendly Name | Type (queue or IVR) | Inbound - Queue to Route To (if call should route directly to a queue) | Studio Flow Name | Phone Number (if the number should just redirect to another outside number) for forwarding to. | Outbound Ring Group(s) | Preferred CNAM | Talkdesk Porting Ticket | Porting Request Date | Porting Status | Latest Status Update | Preliminary Porting Date | Pre-Populate Date | Live | Pre-Configuration Date | Notes | Completed
Nice inContact | 12096052336 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 14087814643 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 14088914030 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 14153689316 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 15037806045 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 15153395354 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 15154992849 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 15179176700 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 15306357688 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 16193015453 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 16508634069 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 17025754430 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 17077185231 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 17077241375 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 17193456503 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 18027930663 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 18587055026 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162155949 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564267 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564543 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564544 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564552 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564554 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162564596 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162650322 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162650817 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162650968 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162650978 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19162744152 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164732486 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164732708 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164732709 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807337 | [9 empty] | 695075 | 2025-01-31 | Pending
| 19164807358 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807379 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807385 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807388 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807389 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19164807397 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19165148747 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19165823639 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166040819 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166044093 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166044558 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166095300 | [9 empty] | 695075 | 2025-01-31 | Pending
| 19166095350 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166643982 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19166776174 | [9 empty] | 695075 | 2025-01-31 | Pending
| 19166785072 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19167590515 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19169933366 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19169935239 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19402310407 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 19494445554 | [9 empty] | 695075 | 2025-01-31 | Pending
Nice inContact | 18336781687 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18443273352 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18443306748 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18443306749 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18443306773 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18446427410 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18446559364 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18446933568 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18447256449 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18662510497 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18662606820 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18662735280 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18663577443 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18663673442 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18665022021 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18665502074 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18665623821 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18665629060 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18667846295 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18667977343 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18668764488 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18669717347 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606871 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606872 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606873 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606874 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606875 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606876 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18772606877 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18882139320 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18882208843 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18882217411 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18882710583 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18883763314 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18883902920 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18884890299 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18884890301 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18884910032 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18884910033 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18885232140 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18885232144 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18885240718 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
| 18885931258 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18886453301 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18886453859 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18886910387 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
| 18887736773 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18889859224 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 18889873443 | [9 empty] | 695075 | 2025-01-31 | Ported | 2025-02-18 | 2025-02-18 | 2025-02-14 |  | 2025-02-17 | Ported into Talkdesk earlier than go live. Currently being forwarded back to Nice inContact
Nice inContact | 17027634882 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466696 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466843 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466856 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466862 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466874 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
Nice inContact | 19162466985 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19162627512 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807300 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807301 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807302 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807303 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807304 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807305 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807306 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807307 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807308 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807309 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807310 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807311 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807312 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807313 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807314 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807315 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807316 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807317 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807318 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807319 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807320 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807321 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807322 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807323 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807324 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807325 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807326 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807327 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807328 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807329 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807330 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807331 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807332 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807333 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807334 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807335 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807336 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807338 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807339 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807340 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807341 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807342 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807343 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807344 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807345 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807346 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807347 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807348 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807349 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807350 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807351 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807352 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807353 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807354 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807355 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807356 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807357 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807359 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807360 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807362 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807363 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807367 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807369 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807370 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807374 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807376 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807377 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807378 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807381 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807382 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807383 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807384 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-20 |  |  |  |  | Reasoning: Unauthorized Signature in the LOA. EGIA needs to follow up with losing carrier.
| 19164807386 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807387 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807390 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807391 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807392 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807393 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807394 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807395 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807396 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807398 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19164807399 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785137 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785179 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785185 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785188 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785189 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785197 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785204 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19166785205 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19168837472 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.
| 19168837473 | [9 empty] | 695075 | 2025-01-31 | Rejected | 2025-02-24 |  |  |  |  | Reason: TN Belongs to Different Accounts". This rejection means that the numbers in your port request belong in different accounts and will need to be separated. To resolve this rejection, please take the following steps: 1. Contact your current carrier(s) to verify and obtain the accounts that your numbers belong to. 2. Reply back to this email with the updated account information that you obtain from your carrier.

## Go Live Issue Tracker (hidden)
Date Reported | Reported By | Issue Description | Priority | Status | Owner | Notes | Resolution | Date Resolved