## UAT Summary
User Story Guide Summary
User Story Guide is complete when all squares are 'green/yes' which signifies Go Live readiness and all Acceptance Criteria has been met
|  |  |  | Overall Tasks Complete: |  | 0 of 38
|  |  |  | Overall Percent Complete: |  | 0% |  |  |  |  | THESE COLUMNS SHOULD BE HIDDEN - DO NOT DELETE COLUMNS OR ROWS
[11 empty] | USER STORIES |  | STUDIO CALL FLOWS
| Talkdesk User Stories | UAT Ready Status | Complete | Open Issues | Completed Tasks | Studio Call Flows | UAT Ready Status | Complete | Open Issues | Completed Tasks | Total Complete | Total Tasks | Total Complete | Total Tasks
| Agent User Stories | Ready for UAT | NO | 0 | 0 of 5 | Main Flow | Ready for UAT | NO | 0 | 0 of 151 | 0 | 5 | 0 | 151
| ManagerSupervisor User Stories | Ready for UAT | NO | 0 | 0 of 8 | [5 empty] | 0 | 8
| Admin User Stories | Ready for UAT | NO | 0 | 0 of 6 | [5 empty] | 0 | 6
| System Requirements | Ready for UAT | NO | 0 | 0 of 11 | [5 empty] | 0 | 11
| Client User Stories | Not Ready for UAT | NO | 0 | 0 of 8 | [5 empty] | 0 | 8
[11 empty] | 0 | 38

## Agent User Stories
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 5
[9 empty] | Total Tasks | 5
[9 empty] | Total Ready | 5
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - Agent and Conversations
Note: This tab contains functions related to agent system readiness and Talkdesk Conversations App |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story As an Agent, I want to be able to...... | Acceptance Criteria / How To Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| Operate standard phone functions while using Conversations | Call another agent directly (agent to agent) | TRUE | FALSE | FALSE
|  | Warm transfer a call to an agent, ring group or external number using Consult* | TRUE | FALSE | FALSE |  |  | *warm transfers to ring groups will only work if an agent is 'Available' in the receiving ring group queue
|  | Hold / Mute functionality | TRUE | FALSE | FALSE
|  | Ability to use a keypad to input digits on an outbound (or inbound) call | TRUE | FALSE | FALSE
| Change my status to a predefined Available/Away/Busy state | In Conversations, select the 'status bar' in the upper right of Workspace and change to a green, yellow, or red state | TRUE | FALSE | FALSE

## ManagerSupervisor User Stories
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 8
[9 empty] | Total Tasks | 8
[9 empty] | Total Ready | 8
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - Managers / Supervisors
Note: This tab contains functions related to Manager/Supervisor tasks |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story As a Manager/Supervisor, I want to..... | Acceptance Criteria / How to Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| Verify INBOUND Calls are being recorded and they can be listened to, downloaded, and generally accessed | Call recordings can be accessed via Activities app | TRUE | FALSE | FALSE
| Verify OUTBOUND Calls are being recorded and they can be listened to, downloaded, and generally accessed | Call recordings can be accessed via Activities app | TRUE | FALSE | FALSE
| Be able to find the interaction ID of a given call for troubleshooting purposes | Interaction ID can be accessed via Activities in Workspace or through various reports (ie. Calls Report, Contacts Report, etc.) | TRUE | FALSE | FALSE |  |  | Alternative Instructions
| Be able to schedule reports/dashboard on a chosen frequency for automation | Reports can be scheduled and delivered as expected | TRUE | FALSE | FALSE |  |  | Schedule a Report and or Dashboard
| Update Agent info (ring groups, roles, etc) Assumes necessary roles/permissions granted to Supervisor's role | Ring groups can be added/removed | TRUE | FALSE | FALSE |  |  | Add/Remove ring groups
| Ability to change/update an Agent's status on the Live Dashboards page | Ability to change an Agent's Status from the Dashboard > Live Agents List widget | TRUE | FALSE | FALSE |  |  | Manager User Status in Live
| Monitor an agent's live call in progress | Ability to monitor/listen/barge into an active agent's call Have any agent place an IB or OB Call Access via Live Dashboards > Live Contacts List > Ellipses | TRUE | FALSE | FALSE |  |  | Monitor/Barge on a Live Call
| Create a Live dashboard | Create/Edit Live Dashboard | TRUE | FALSE | FALSE |  |  | Create/Edit Live Dashboard

## Admin User Stories
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 6
[9 empty] | Total Tasks | 6
[9 empty] | Total Ready | 6
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - Administrators
Note: This tab contains functions related to Admin/Supervisor tasks and assumes you have the appropriate roles/permissions |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story As an Administrator, I want to..... | Acceptance Criteria / How to Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| Create a new user | Agent successfully created and can access Talkdesk; Talkdesk Classic > Admin > Agents | TRUE | FALSE | FALSE
| Create and manage Teams | Teams can be created and updated; Agents can be assigned to Teams (1:1); Talkdesk Classic > Teams | TRUE | FALSE | FALSE
| Create, manage, and update Studio flows Includes changing Holidays / Business Hours | Flows can be modified and updated as necessary Talkdesk Classic > Admin > Studio | TRUE | FALSE | FALSE
| Purchase and manage phone numbers | Ability to purchase new or modify existing phone numbers Talkdesk Classic > Admin > Numbers | TRUE | FALSE | FALSE
| Become familiar with other Admin sections of TD Main | Dispositions Roles and Permissions Managing automations within integrations Preferences | TRUE | FALSE | FALSE
| Ability to change an Agent/User's role for elevated/reduce permissions | Users roles can be updated | TRUE | FALSE | FALSE |  |  | Update Users Role

## System Requirements
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 11
[9 empty] | Total Tasks | 11
[9 empty] | Total Ready | 11
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - System Requirements
Note: This tab contains functions and features related to the Talkdesk minimum System Requirements |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story / Requirement | Acceptance Criteria / How to Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| Confirm agents have adequate bandwidth to handle audio clearly through headsets | Have agents place or accept test calls and confirm clean and clear audio (minimum 10 tests with various agents/phones) | TRUE | FALSE | FALSE
| Complete any relevant network tests to confirm bandwidth for Audio and Applications to function correctly | Network Tests Validated by Talkdesk engineers No identified latency variations or issues with network bandwidth | TRUE | FALSE | FALSE
| Clear cache/cookies and set Chrome as default browser for all users; Remove any unnecessary Extensions | Chrome is default Agent browser and all unnecessary extensions removed | TRUE | FALSE | FALSE
| Allow Microphone Access in Browser to enable Audio in Conversations | Two way audio is confirmed in Conversations (inbound and outbound calls) | TRUE | FALSE | FALSE |  |  | Setup Browser to work with Talkdesk
| Allow/Enable Desktop Notifications (optional) | Desktop notifications enabled and working when a call comes inbound | TRUE | FALSE | FALSE |  |  | Enable Desktop Notifications
| CX Cloud Installation on all agent machines | CX Cloud installed and agents can log in | TRUE | FALSE | FALSE |  |  | How to install CX Cloud
| Click to call a contact from a CRM or webpage via the TD Click to Call Extension (if click to call is applicable) | Calls are delivered through Conversations when clicking on them (note: must be a telephone formatted phone number; alternatively, use 'right click to call' if the number is not in hyperlink format) | TRUE | FALSE | FALSE |  |  | Install Click to Call Extension
| Confirm API access is granted within your application and/or Postman | Successfully able to generate a token and/or execute a Talkdesk API call | TRUE | FALSE | FALSE
| Visually confirm all roles/permissions are correctly assigned (including after call work settings) | All roles/permissions correctly configured and assigned to the appropriate agents | TRUE | FALSE | FALSE
| Visually confirm all users/agents have been created and have the appropriate ring groups and role assigned | All agents are configured and ready for Go Live | TRUE | FALSE | FALSE
| Visually confirm all Talkdesk Admin > Preferences have been set appropriately | All settings appropriately configured | TRUE | FALSE | FALSE

## Client User Stories
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 8
[9 empty] | Total Tasks | 8
[9 empty] | Total Ready | 0
[9 empty] | UAT Ready Status | Not Ready for UAT
User Stories - Client User Stories
|  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story As an Agent, I want to be able to...... | Acceptance Criteria / How To Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| user stories created during implementation based on use cases |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE

## Main Flow
THESE ROWS SHOULD BE HIDDEN | [8 empty] | THESE COLUMNS SHOULD BE HIDDEN
[9 empty] | Complete | NO
[9 empty] | Open Issues | 0
[9 empty] | Total Complete | 0
[9 empty] | Completed Tasks | 0 of 151
[9 empty] | Total Tasks | 151
[9 empty] | Total Ready | 151
[9 empty] | UAT Ready Status | Ready for UAT
User Stories - Audience / Callers
Note: This tab contains functions related to callers using the Studio Flow (IVR) |  |  |  | FALSE | This box will be checked automatically once all Acceptance Criteria on the page has passed.
ID | User Story | Acceptance Criteria / How to Test | Ready for Testing | Passed | Failed | Tester Name | Error Info / Notes | Talkdesk Notes
| As a caller, I want to be able to...... | Testing/Temporary Numbers: 215 607 2929
Before beginning testing please make sure you have the document, Incoming_ProgramNumbers open, as this will have the temporary Talkdesk Number associated to each program, as well as the email address in which you should recieve voicemails at. This document will be broken up into sections, the first section pertains to Business Hours, the second to Holidays, the third to Open, the forth to the Autopilot
| Leave a voicemail for smud | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE |  |  | * Refer to the UAT Update file for more guidelines and support.
| Leave a voicemail for loan enrollment | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Geary_Pacific_ComfyCA | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for SVP | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Carrier_Bryant_ICP | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Rheem_Ruud | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for contractor services | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for East_Coast_Metals | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for LG | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Go_Green | With the contractor services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for JEA_Residential | With the customer service ec hours hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for WSIP | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Clean_Air | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Southwest_Gas | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Lennox | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Atmos_Energy | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Info | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for CA_Turf | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Receptionist | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Anaheim_Residential | With the customer services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Dealer_Rebates | With the dealer rebates hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Progrm_Solution_Dist_Sprt_2 | With the dealer rebates hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Program_Solution_Dist_Sprt | With the dealer rebates hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Foundation | With the egia foundation hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Tech_Help | With the IT Help hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for OPTIMUS | *note there are two numbers to be called for optimus please call both temporary numbers With the loan enrollment hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for OPTIMUS | *note there are two numbers to be called for optimus please call both temporary numbers With the loan enrollment hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Trane_MBA | With the member services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for American_Standard_MBA | With the member services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Events_Services | With the member services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Member_Services | With the member services hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for smud | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE |  |  | * Refer to the UAT Update file for more guidelines and support.
| Leave a voicemail for loan enrollment | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Geary_Pacific_ComfyCA | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for SVP | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Carrier_Bryant_ICP | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Rheem_Ruud | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for contractor services | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for East_Coast_Metals | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for LG | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Go_Green | With the contractor services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for JEA_Residential | With the customer service ec holiday hours module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for WSIP | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Clean_Air | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Southwest_Gas | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Lennox | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Atmos_Energy | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Info | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for CA_Turf | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Receptionist | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Anaheim_Residential | With the customer services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Dealer_Rebates | With the dealer rebates holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Progrm_Solution_Dist_Sprt_2 | With the dealer rebates holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Program_Solution_Dist_Sprt | With the dealer rebates holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Foundation | With the egia foundation holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Tech_Help | With the IT Help holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for OPTIMUS | *note there are two numbers to be called for optimus please call both temporary numbers With the loan enrollment holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for OPTIMUS | *note there are two numbers to be called for optimus please call both temporary numbers With the loan enrollment holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Trane_MBA | With the member services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for American_Standard_MBA | With the member services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Events_Services | With the member services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Leave a voicemail for Member_Services | With the member services holiday module set to closed, call into the temporary number assigned to the queue. Leave a voicemail and verify if the correct email inbox received the notification and the voicemail was assigned to the correct queue | TRUE | FALSE | FALSE
| Speak to someone queued for Anaheim_Residential | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 | TRUE | FALSE | FALSE
| Speak to someone queued for Anaheim_Spanish_Residential | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 | TRUE | FALSE | FALSE
| Have a call transfered out to commercial | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Leave a voicemail for Anaheim_Residential | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 While in queue press option 1 | TRUE | FALSE | FALSE
| Leave a voicemail for Anaheim_Spanish_Residential | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 While in queue press option 1 | TRUE | FALSE | FALSE
| Speak to Nathaniel Odum | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 1 | TRUE | FALSE | FALSE
| Speak to Jose valadez | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 2 | TRUE | FALSE | FALSE
| Speak to Clinton Cramer | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 3 | TRUE | FALSE | FALSE
| Speak to Eddie Javaid | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 4 | TRUE | FALSE | FALSE
| Speak to Maria Alatorre | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 5 | TRUE | FALSE | FALSE
| Speak to someone queued for IT_Tech_Help | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 3 | TRUE | FALSE | FALSE
| Leave a voicemail for Anaheim_Residential | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 3 While in queue press option 1 | TRUE | FALSE | FALSE
| Speak to someone based on extension IT FLOW | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Key in the digit extension for that specific person | TRUE | FALSE | FALSE
| Speak to someone based on extension OPTIMUS FLOW | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Key in the digit extension for that specific person | TRUE | FALSE | FALSE
| Speak to someone queued for loan enrollment | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for optimus | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 3 Press options 1 2 3 4 5 or 0 | TRUE | FALSE | FALSE
| Speak to someone queued for optimus | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 4 Press options 1 2 3 4 5 or 0 | TRUE | FALSE | FALSE
| Have a call transfered out to greensky | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 1 | TRUE | FALSE | FALSE
| Have a call transfered out to wellsfargo | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 2 | TRUE | FALSE | FALSE
| Have a call transfered out to ftl | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 3 | TRUE | FALSE | FALSE
| Have a call transfered out to foundation | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 4 | TRUE | FALSE | FALSE
| Have a call transfered out to advantage alliance | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 5 | TRUE | FALSE | FALSE
| Have a call transfered out to microve | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 6 | TRUE | FALSE | FALSE
| Have a call transfered out to optimus | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Press option 7 | TRUE | FALSE | FALSE
| Leave a voicemail for optimus | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 4 While in queue press option 1 | TRUE | FALSE | FALSE
| Speak to someone queued for EGIA_Foundation | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for WSIP | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Clean_Air | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Member_Services | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Lennox | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Atmos_Energy | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for EGIA_Info | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for JEA_Residential | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Go_Green | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Clean_Power_Alliance | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Foundation | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for WSIP | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Clean_Air | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Member_Services | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Lennox | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Atmos_Energy | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Info | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for JEA_Residential | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Go_Green | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Leave a voicemail for Clean_Power_Alliance | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). | TRUE | FALSE | FALSE
| Speak to someone queued for Trane_MBA | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for American_Standard_MBA | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Loan_Enrollment | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Events_Services | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Geary_Pacific_ComfyCA | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Carrier_Bryant_ICP | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Rheem_Ruud | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Contractor_services | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Dealer_Rebates | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for East_Coast_Metals | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Southwest_Gas | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Progrm_Solution_Dist_Sprt_2 | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for Program_Solution_Dist_Sprt | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Leave a voicemail for EGIA_Foundation | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Trane_MBA | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for American_Standard_MBA | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Loan_Enrollment | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Events_Services | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Geary_Pacific_ComfyCA | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Carrier_Bryant_ICP | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Rheem_Ruud | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for East_Coast_Metals | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Contractor_services | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Dealer_Rebates | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Southwest_Gas | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Progrm_Solution_Dist_Sprt_2 | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for Program_Solution_Dist_Sprt | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 Press option 1 while in queue | TRUE | FALSE | FALSE
| Speak to someone based on extension P2 FLOW | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Key in the digit extension for that specific person | TRUE | FALSE | FALSE
| Speak to someone queued for SMUD | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 | TRUE | FALSE | FALSE
| Speak to someone queued for SVP | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 | TRUE | FALSE | FALSE
| Speak to someone queued for LG | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 | TRUE | FALSE | FALSE
| Leave a voicemail for SMUD | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for SVP | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for LG | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 Press option 1 while in queue | TRUE | FALSE | FALSE
| Leave a voicemail for SMUD | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Leave a voicemail for SVP | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Leave a voicemail for LG | Set all agents to unavailable With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for member_services | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 1 | TRUE | FALSE | FALSE
| Speak to someone queued for optimus | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 2 | TRUE | FALSE | FALSE
| Speak to someone queued for dealer_rebates | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 3 | TRUE | FALSE | FALSE
| Speak to someone queued for reception | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 4 | TRUE | FALSE | FALSE
| Speak to someone based on extension IT FLOW | With all of the time of day modules and calendar modules set to open, call into the temporary number assigned to the skill(s). Press option 5 Key in the digit extension for that specific person | TRUE | FALSE | FALSE
| Check rebate status Socal | In order to test the rebate status' properly before beginning identify 5 qualifying users for the following scenarios Turf = Y Program Type = Residential Turf = N Program Type = Residential Turf = Y Program Type = Commercial Turf = N Program Type = Commercial A user with multiple rebates To test each of the following scenarios is the same, first within the automation designer change the package content to user's ANI you want to test with After this is complete, call into the Socal temporary number and when prompted say "rebate status" Key in the users zipcode followed by the pound sign Verify that information is correctly displayed If testing a user with multiple rebates say next to cycle through the rebates until you find the one you want then say this one. After you have found the rebate you want say "agent" and verify it routes to the proper queue "met_general, met_commericial, etc." | TRUE | FALSE | FALSE
| Check rebate status Tampa | In order to test the rebate status' properly before beginning identify 3 qualifying users for the following scenarios Turf = T Program Type = Residential Turf = T Program Type = Commercial A user with multiple rebates To test each of the following scenarios is the same, first within the automation designer change the package content to user's ANI you want to test with After this is complete, call into the Tampa temporary number and when prompted say "rebate status" Key in the users zipcode followed by the pound sign Verify that information is correctly displayed If testing a user with multiple rebates say next to cycle through the rebates until you find the one you want then say this one. After you have found the rebate you want say "agent" and verify it routes to the proper queue "tbw_res, etc." | TRUE | FALSE | FALSE

## Color Identifier
Contractor Services
Customer Service EC
Customer Services
Dealer Rebates
EGIA Fodunation
IT Help
Loan Enrollment
Member Services
Anaheim
IT Flow
OPTIMUS
P1
P2
P2VM
Reception
Tampa
Socal